## Lessons Learned
LESSON LEARNED
DOCUMENT VERSION: 1.0
PROJECT NAME |  | campus finder |  |  | PLEASE GO THROUGH THE INSTRUCTION SHEET PROVIDED TO GET AN UNDERSTANDING OF HOW TO USE THIS TEMPLATE.
PROJECT ID |  | IP-11170
PROJECT MANAGER |  | Sravya Tepada
PROJECT SPONSOR |  | Tushar Topale
SL. NO | DATE RAISED | EVENT | LESSON CATEGORY | EARLY WARNING SIGNS? | RECOMMENDATIONS | ACTIONS | OWNER | STATUS | ADDITIONAL COMMENTS
| MENTION THE DATE ON WHICH THE MATTER WAS RAISED | DESCRIBE THE EVENT THAT WAS RAISED | MENTION WHICH CATEGORY THE EVENT WAS RELATED TO | MENTION YES OR NO | MENTION THE RECOMMENDATIONS THAT WAS SUGGESTED FOR SOLVING THE EVENT IF ANY | MENTION THE ACTION SELECTED FOR SOLVING THE EVENT | MENTION THE RESPONSIBLE PERSON FOR SOLVING THE EVENT | SOLVED/PENDING | MENTION IF ANYTHING ELSE OCCURRED DURING THE TIME OF THE MENTIONED EVENT
1 | 17-Apr-2026 | Early stakeholder alignment meeting alignment session prevented major scope changes later in the project. | Planning | NO | Conduct a mandatory stakeholder kickoff meeting in Week 1 of every project. | Held kickoff meeting in Week 1 with sponsor and manager; documented minutes. | Harshada Topale | SOLVED | WENT WELL: Prevented scope creep early on.
2 | 25-Apr-2026 | Developers had to make many UI decisions on their own, leading to rework due to high-level wireframes only. | Planning | YES | Detailed Figma wireframes and clickable prototypes must be signed off before coding starts. | Held design review sessions using low/high fidelity wireframes in Figma. | moulik | SOLVED | IMPROVE: Rework was required on several pages.
3 | 30-Apr-2026 | Timeline underestimated role-based access control complexity; API took 40% longer. | Planning | YES | Backend security tasks must include a minimum of 20% buffer in scheduling. | Updated WBS to incorporate explicit tasks for JWT auth and security testing buffers. | moulik | SOLVED | IMPROVE: Delayed initial backend sprints.
4 | 08-May-2026 | Building reusable React/FastAPI shared components saved significant development time. | Design | NO | Invest in a shared component library and design system in early design phases. | Created a reusable components folder in frontend repo for buttons, forms, and cards. | moulik | SOLVED | WENT WELL: Speeded up UI development by 30%.
5 | 12-May-2026 | ER diagram and schema normalisation prevented duplicate data and complex query bugs. | Design | NO | Review ER diagrams with technical lead prior to writing database migrations. | Held team review for PostgreSQL migrations to ensure normalisation standards. | moulik | SOLVED | WENT WELL: Zero data inconsistency issues arose.
6 | 15-May-2026 | Accessibility was not designed in; final review required reworking 12 components. | Design | YES | Add WCAG accessibility standards (ARIA, color contrast) to component Definition of Done. | Integrated axe-core scans into development workflow and fixed color contrasts. | moulik | SOLVED | IMPROVE: Accessibility should be a design priority.
7 | 20-May-2026 | Docker Compose setup eliminated local database/Node version mismatch issues. | Development | NO | Containerise developer environments from Day 1 using Docker Compose. | Added docker-compose.yml to local environment configuration and README. | moulik | SOLVED | WENT WELL: Saved hours of environment debugging.
8 | 22-May-2026 | Git Flow branching strategy kept codebase stable with zero accidental master merges. | Development | NO | Enforce branch protections and a strict branching model (main/develop/feature). | Implemented GitHub branch rules requiring approved pull requests. | moulik | SOLVED | WENT WELL: Codebase remained deployable at all times.
9 | 28-May-2026 | Mandatory peer code reviews caught 23 bugs, including 3 security issues, before testing. | Development | NO | Require at least one peer approval for every pull request with a checklist. | Set up pull request templates outlining code quality and security criteria. | moulik | SOLVED | WENT WELL: Raised team knowledge sharing.
10 | 01-Jun-2026 | Daily standup meetings kept the remote team aligned and surfaced blockers early. | Communication | NO | Hold structured, 15-minute daily standups utilizing a shared Kanban board. | Conducted daily standups on Teams and tracked blockers on Trello boards. | Harshada Topale | SOLVED | WENT WELL: Resolved 4 critical scheduling risks.
11 | 05-Jun-2026 | Inconsistent API error payload formats caused frontend integration errors. | Development | YES | Establish a global API response schema envelope before writing backend endpoints. | Enforced standard error structures using FastAPI response models. | moulik | SOLVED | IMPROVE: Wasted 2 days debugging integration.
12 | 10-Jun-2026 | Lack of onboarding developer documentation delayed new team member by 3 days. | Communication | YES | Maintain an up-to-date setup guide, contribution guide, and API docs in repository. | Created setup guides and auto-generated Swagger endpoint documentation. | moulik | SOLVED | IMPROVE: Onboarding docs must be written on Day 1.
13 | 12-Jun-2026 | Scope management and formal change controls deflected 80% of out-of-scope requests. | Project Management | NO | Establish signed scope statement and strict change request procedure from start. | Used a change control template to push non-critical features to Phase 2. | Harshada Topale | SOLVED | WENT WELL: Maintained original launch timeline.
14 | 15-Jun-2026 | Risk register was created at kickoff but was never updated, leading to surprise issues. | Project Management | YES | Integrate a weekly risk register review as a fixed agenda item in status meetings. | Updated the RAID log weekly with ownership and mitigation tracking. | Harshada Topale | SOLVED | IMPROVE: Risk log must be a living document.
15 | 20-Jun-2026 | Low unit test coverage (42%) led to regression bugs during final refactoring. | Testing | YES | Enforce a code coverage minimum (e.g. 80%) in pipeline before merging. | Set up Jest and Pytest coverage tools in CI pipeline configuration. | moulik | SOLVED | IMPROVE: Led to unplanned bug-fixing loops.
16 | 22-Jun-2026 | Centralised Postman collection committed to repository saved frontend/backend testing effort. | Testing | NO | Version control and share API testing collections across the development team. | Exported updated Postman collection file to git repository on backend updates. | moulik | SOLVED | WENT WELL: Maintained API contract sync.
17 | 28-Jun-2026 | Performance test conducted in final week revealed severe course listing API bottleneck. | Testing | YES | Integrate automated API performance benchmark scans from mid-sprint. | Added k6 load test run files and optimised database indexes. | moulik | SOLVED | IMPROVE: Delayed go-live schedule by 3 days.
18 | 29-Jun-2026 | Safari-specific CSS rendering issues were discovered late in the testing cycle. | Testing | YES | Include cross-browser test runner runs in developers' local verification steps. | Utilised Playwright multi-browser test runners to automate cross-browser verification. | moulik | SOLVED | IMPROVE: CSS flexbox and grid issues fixed in hotfix.
19 | 08-Jul-2026 | Manual staging deployments took 45 minutes and led to configuration mistakes. | Deployment | YES | Automate deployment using CI/CD pipelines from the first development week. | Created GitHub Actions workflow to run lint, test, build, and automatic deploy. | moulik | SOLVED | WENT WELL: Deployment time cut down to 8 minutes.
20 | 09-Jul-2026 | Hardcoded local backend URL in code caused production outage of 35 minutes. | Deployment | YES | Ensure environment configurations are strictly separated using .env files. | Moved all secrets and backend URLs to environment variables. | moulik | SOLVED | IMPROVE: Caused client outage due to wrong API target.