## GPI - Project Charter
PROJECT CHARTER
GENERAL PROJECT INFORMATION
PROJECT NAME | campus finder(premium college search & discovery plat form)
PROJECT SPONSOR | Tushar Topale
PROJECT MANAGER | Harshada Topale
EXPECTED START DATE | 04-15-2026
EXPECTED COMPLETION DATE | 07-15-2026
ESTIMATED COST | N.A.
GOALS, OBJECTIVES, DELIVERABLES
PROJECT OBJECTIVE (Objective of a project represents the output or what you want to accomplish by doing it.) | Develop and deploy a high-performance, premium web platform for Indian students to search, filter, and discover colleges. The platform supports side-by-side college comparisons, an admission eligibility predictor based on entrance exams (JEE, NEET, 12th percentage), and an admin panel to manage enquiries and add listings
BUSINESS CASE (A business case provides justification for undertaking a project. It evaluates the benefit, cost and risk of alternative options and provides a rationale for the preferred solution. ) | Develop and deploy a high-performance, premium web platform for Indian students to search, filter, and discover colleges. The platform supports side-by-side college comparisons, an admission eligibility predictor based on entrance exams (JEE, NEET, 12th percentage), and an admin panel to manage enquiries and add listings
GOALS/METRICS (The project goal refers to achieving a desired outcome (performance goal) at a specific end date (time goal) employing a specific amount of resources (resource goal).) | Develop and deploy a high-performance, premium web platform for Indian students to search, filter, and discover colleges. The platform supports side-by-side college comparisons, an admission eligibility predictor based on entrance exams (JEE, NEET, 12th percentage), and an admin panel to manage enquiries and add listings
EXPECTED DELIVERABLES (Describe the quantifiable goods or services that must be provided upon the completion of a project.) | • Express.js REST API server (server.js). • SQLite relational database schema and seed data (database.js, database.sqlite, seed.js). • Responsive single-page application frontend (index.html, style.css, app.js). • Secured Admin Panel for lead monitoring and college additions (admin.html, admin.js). • Setup guides, database query logs, and code documentation
PROJECT SCOPE AND SCHEDULE
WITHIN SCOPE (This is functions and information which should be taken into account(estimated) in the development at the first stage. Or the stage for the development perios.) | • Database schema mapping (Colleges, Courses, Placements, Facilities, and Contact Details). • Search and filter REST API endpoints (/api/colleges). • Score-to-admission predictor logic for JEE, NEET, and 12th board percentage (/api/predictor). • Side-by-side comparison endpoint (/api/colleges/compare). • Lead submission form (/api/enquiries) and admin panel for enquiry management. • Adding/updating college records through admin panel forms. • Premium Vanilla CSS responsive user interface layout.
OUTSIDE OF SCOPE (This is functions which are planned to be done, but they are not reqired on the first stages.) | • Real-time online chat counseling or video consultations. • Payment gateway integration for college application fees. • Student registration profiles (kept anonymous to lower access barriers)
PROJECT RESOURCES AND COSTS
PROJECT TEAM (Mention the number of resources, who will be working on the project.) | Project Team: • Project Sponsor: Tushar Topale (Executive supervision) • Project Manager / Process Owner: Harshada Topale (Acceptance testing, schedule tracking) • Intern / Developer: Purna Sai Venkat (Database schema, Express backend, Vanilla JS frontend)
SUPPORT RESOURCES (Mention all the other resources that will be needed for the completion of the project.) | Support Resources: Node.js runtime environment (v18+), SQLite3 database tools, browser testing environments.
COST ALLOCATION (Mention the cost of all the resources on an hourly/monthly/yearly basis. This will help to stick on to the project budget.) | Cost Allocation: Intern stipend covered under academic internship guidelines. Software/Tools: $0 (using a 100% open-source stack)
PROJECT STAKEHOLDERS AND CUSTOMERS
PROCESS OWNER (Mention the Project Owner) | Process Owner: Harshada Topale
KEY STAKEHOLDERS (Mention all the stake holders involved in the project.) | Key Stakeholders: Tushar Topale (Sponsor), Harshada Topale (PM), Purna Sai Venkat (Intern), Partnering Indian Colleges & Universities.
END CUSTOMER (Mention the client name.) | End Customer: Indian high school graduates, university aspirants, parents, and educational counselors.
PROJECT RISKS, CONSTRAINTS, ASSUMPTIONS
RISKS (Risk is any unexpected event that can affect your project — for better or for worse. Risk can affect anything: people, processes, technology, and resources.) | Risks: 1. Dynamic Cutoffs: Cutoffs shift yearly, meaning predictor rankings are only advisory guidelines. (Mitigation: Clear disclaimer messaging.) 2. Data Maintenance: Keeping tuition and placement stats current. (Mitigation: Admin portal enabling rapid insertions/edits.
ASSUMPTIONS (An assumption is any project factor that is considered to be true, real, or certain without empirical proof or demonstration.) | Assumptions: Users have an active internet connection and the SQLite database is pre-seeded.
CONSTRAINTS (Project constraints are anything that restricts or dictates the actions of the project team.) | Constraints: Must run locally or on basic server runtimes without complex cloud database architectures. Schedule: April 15, 2026 to July 15, 2026.
MILESTONES
MILESTONE 1- Requirement Gathering ("Mention Completion Date in MM-DD-YYYY format. Requirement gathering is marked as complete after submission of SRS document") | 04-25-2026 Complete after database seeding (database.sqlite) and core routing/page coding completion. Complete after submission of the Software Requirements Specification (SRS) document.
MILESTONE 2 - Planning ("Mention Completion Date in MM-DD-YYYY format. Planning phase is considered after a duly completed Work Breakdown Structure (WBS), Project Schedule and RAID logs") | 05-05-2026 Complete after WBS, Project Schedule, and RAID logs are compiled.
MILESTONE 3 - Design ("Mention Completion Date in MM-DD-YYYY format. Design stage is considered complete after submission of Design Specifications and Wireframe files") | 05-20-2026 Complete after submission of Design Specifications and Wireframe files
MILESTONE 4 - Development ("Mention Completion Date in MM-DD-YYYY format. Development stage is considered complete after submission of Design Specifications and Wireframe files") | Complete after database seeding (database.sqlite) and core routing/page coding completion.06-18-2026
MILESTONE 5 - Testing ("Mention Completion Date in MM-DD-YYYY format. Testing stage is considered complete after submission of Test Reports") | 07-02-2026 Complete after submission of route check logs, database queries, and frontend verification test reports
MILESTONE 6 - Deployment ("Mention Completion Date in MM-DD-YYYY format. Deployment stage is considered complete after sybmitting the ") | 07-09-2026 Complete after project handover report, installation guides, and lessons learned logs.
MILESTONE 7 - Closure ("Mention Completion Date in MM-DD-YYYY format. Project closure is considered complete after handover of leasson learnt log, project report and installation guide") | 07-15-2026Complete after project handover report, installation guides, and lessons learned logs.