## Project Schedule
IAC Internship Program 2023 - WEB DEVELOPMENT Project Schedule
| PROJECT START DATE |  | Wed, 15-Apr-26 | (Enter the date you started working on your project)
| Display Week Sr No |  | 1
Should you face any difficulty in completing the 'Project Schedule', please refer to 'Project Planning' Workshop https://script.google.com/macros/s/AKfycbz1vCRZzDZf95kwXBgy1DzKe59fupHWWtehSUu0jeTsIZZxn3YdNVAD1sHDLDuanb...
Sr No | Week/Date | Activities | Task | Sub Task | Dependencies | Assigned to | Start Date | End Date | Actual End Date | Hours required | Status | Progress | Comments
1 | Week 1: Requirement Gathering
1.1 |  | Requirement Elicitation |  |  |  |  | 15-Apr-26 | 21-Apr-26 | 21-Apr-26 |  | Completed | 100%
1.1.1 |  | Requirement Elicitation | Conduct sessions with PM & Sponsor |  |  | moulik | 15-Apr-26 | 18-Apr-26 | 18-Apr-26 | 12 | Completed | 100% | Completed on schedule
1.1.2 |  | Requirement Elicitation | Research existing LMS solutions |  |  | moulik | 18-Apr-26 | 21-Apr-26 | 21-Apr-26 | 8 | Completed | 100% | Completed on schedule
1.2 |  | SRS Preparation |  |  |  |  | 15-Apr-26 | 21-Apr-26 | 21-Apr-26 |  | Completed | 100%
1.2.1 |  | SRS Preparation | Write Functional Requirements |  |  | moulik | 15-Apr-26 | 17-Apr-26 | 17-Apr-26 | 16 | Completed | 100% | SRS Document Drafted
1.2.2 |  | SRS Preparation | Define Non-Functional Requirements |  |  |  | 17-Apr-26 | 19-Apr-26 | 19-Apr-26 | 12 | Completed | 100% | Performance/Security metrics
1.2.3 |  | SRS Preparation | Draft Use Cases and Diagrams |  | 1.1.1 | moulik | 19-Apr-26 | 21-Apr-26 | 21-Apr-26 | 16 | Completed | 100% | Diagrams completed
2 | Week 2: Planning & Onboarding
2.1 |  | Project Planning |  |  |  |  | 22-Apr-26 | 28-Apr-26 | 28-Apr-26 |  | Completed | 100%
2.1.1 |  | Project Planning | Create WBS (Work Packages) |  | 1.2.1 |  | 22-Apr-26 | 25-Apr-26 | 25-Apr-26 | 16 | Completed | 100% | WBS mapped successfully
2.1.2 |  | Project Planning | Draft Project Schedule & Gantt |  | 2.1.1 |  | 25-Apr-26 | 28-Apr-26 | 28-Apr-26 | 12 | Completed | 100% | Schedule established
2.2 |  | Environment Setup |  |  |  |  | 22-Apr-26 | 28-Apr-26 | 28-Apr-26 |  | Completed | 100%
2.2.1 |  | Environment Setup | Setup GitHub Repo & Git Flow |  |  | moulik | 22-Apr-26 | 25-Apr-26 | 25-Apr-26 | 8 | Completed | 100% | Branch protections active
2.2.2 |  | Environment Setup | Establish coding standards & PRs |  |  |  | 25-Apr-26 | 28-Apr-26 | 28-Apr-26 | 8 | Completed | 100% | PR templates configured
3 | Week 3: Architecture & UI Design
3.1 |  | UI/UX Design |  |  |  |  | 29-Apr-26 | 05-May-26 | 05-May-26 |  | Completed | 100%
3.1.1 |  | UI/UX Design | Design low-fidelity homepage |  | 1.2.3 | moulik | 29-Apr-26 | 02-May-26 | 02-May-26 | 16 | Completed | 100% | Wireframes in Figma
3.1.2 |  | UI/UX Design | Create color scheme & style guide |  | 3.1.1 |  | 02-May-26 | 05-May-26 | 05-May-26 | 12 | Completed | 100% | Branding guide ready
3.2 |  | Database Design |  |  |  |  | 29-Apr-26 | 05-May-26 | 05-May-26 |  | Completed | 100%
3.2.1 |  | Database Design | Define PostgreSQL ER diagram |  |  | moulik | 29-Apr-26 | 02-May-26 | 02-May-26 | 16 | Completed | 100% | 9 tables normalised
3.2.2 |  | Database Design | Write schema migration scripts |  | 3.2.1 | moulik | 02-May-26 | 05-May-26 | 05-May-26 | 12 | Completed | 100% | Alembic setup done
4 | Week 4: API Design & Prototyping
4.1 |  | API Contract Design |  |  |  |  | 06-May-26 | 12-May-26 | 12-May-26 |  | Completed | 100%
4.1.1 |  | API Contract Design | Define endpoints & schemas |  | 3.2.1 | moulik | 06-May-26 | 09-May-26 | 09-May-26 | 20 | Completed | 100% | 22 REST endpoints
4.1.2 |  | API Contract Design | Write API Swagger specifications |  | 4.1.1 | moulik | 09-May-26 | 12-May-26 | 12-May-26 | 12 | Completed | 100% | Swagger YAML generated
4.2 |  | UI Review |  |  |  |  | 06-May-26 | 12-May-26 | 12-May-26 |  | Completed | 100%
4.2.1 |  | UI Review | Conduct wireframe reviews |  | 3.1.1 |  | 06-May-26 | 09-May-26 | 09-May-26 | 12 | Completed | 100% | PM feedback integrated
4.2.2 |  | UI Review | Implement UI feedback in Figma |  | 4.2.1 | moulik | 09-May-26 | 12-May-26 | 12-May-26 | 16 | Completed | 100% | 12 design tweaks applied
5 | Week 5: Dev - Setup & Auth
5.1 |  | Dev Setup |  |  |  |  | 13-May-26 | 19-May-26 | 19-May-26 |  | Completed | 100%
5.1.1 |  | Dev Setup | Configure Docker Compose files |  | 2.2.1 | moulik | 13-May-26 | 16-May-26 | 16-May-26 | 12 | Completed | 100% | Identical dev environment
5.1.2 |  | Dev Setup | Configure pre-commit hooks |  | 2.2.2 | moulik | 16-May-26 | 19-May-26 | 19-May-26 | 8 | Completed | 100% | ESLint & Prettier active
5.2 |  | Auth Backend |  |  |  |  | 13-May-26 | 19-May-26 | 19-May-26 |  | Completed | 100%
5.2.1 |  | Auth Backend | Build JWT login & register API |  | 4.1.1 | moulik | 13-May-26 | 17-May-26 | 17-May-26 | 24 | Completed | 100% | Secure hashing used
5.2.2 |  | Auth Backend | Configure connection pooling |  | 3.2.2 | moulik | 17-May-26 | 19-May-26 | 19-May-26 | 8 | Completed | 100% | PostgreSQL pool limit
6 | Week 6: Dev - Auth UI & Homepage
6.1 |  | Auth Frontend |  |  |  |  | 20-May-26 | 26-May-26 | 26-May-26 |  | Completed | 100%
6.1.1 |  | Auth Frontend | Build login & register screen UI |  | 4.2.2 | moulik | 20-May-26 | 23-May-26 | 23-May-26 | 16 | Completed | 100% | Forms validation added
6.1.2 |  | Auth Frontend | Integrate JWT token storage |  | 5.2.1 | moulik | 23-May-26 | 26-May-26 | 26-May-26 | 12 | Completed | 100% | Redirection flow ready
6.2 |  | Homepage UI |  |  |  |  | 20-May-26 | 26-May-26 | 26-May-26 |  | Completed | 100%
6.2.1 |  | Homepage UI | Build banner & core nav header |  | 3.1.2 | Sunay Potnuru | 20-May-26 | 26-May-26 | 26-May-26 | 18 | Completed | 100% | Fully responsive
7 | Week 7: Dev - Course Catalog
7.1 |  | Course Catalog Dev |  |  |  |  | 27-May-26 | 02-Jun-26 | 02-Jun-26 |  | Completed | 100%
7.1.1 |  | Course Catalog Dev | Develop course catalog grid UI |  | 6.2.1 |  | 27-May-26 | 30-May-26 | 30-May-26 | 16 | Completed | 100% | Grid styles and pagination
7.1.2 |  | Course Catalog Dev | Write backend search & filter API |  | 5.2.2 | moulik | 30-May-26 | 02-Jun-26 | 02-Jun-26 | 16 | Completed | 100% | Full-text search enabled
7.2 |  | DB Seeding |  |  |  |  | 27-May-26 | 02-Jun-26 | 02-Jun-26 |  | Completed | 100%
7.2.1 |  | DB Seeding | Seed DB with 10 course records |  | 3.2.2 | moulik | 27-May-26 | 02-Jun-26 | 02-Jun-26 | 8 | Completed | 100% | Seed courses script active
8 | Week 8: Dev - Enrollment & Detail
8.1 |  | Enrollment Dev |  |  |  |  | 03-Jun-26 | 09-Jun-26 | 09-Jun-26 |  | Completed | 100%
8.1.1 |  | Enrollment Dev | Build course enrollment endpoint |  | 7.1.2 | moulik | 03-Jun-26 | 06-Jun-26 | 06-Jun-26 | 16 | Completed | 100% | Enroll record added to DB
8.1.2 |  | Enrollment Dev | Build course progress logic |  | 8.1.1 | moulik | 06-Jun-26 | 09-Jun-26 | 09-Jun-26 | 16 | Completed | 100% | Lesson checkpoint tracker
8.2 |  | Course Detail UI |  |  |  |  | 03-Jun-26 | 09-Jun-26 | 09-Jun-26 |  | Completed | 100%
8.2.1 |  | Course Detail UI | Develop detail view with syllabus |  | 7.1.1 |  | 03-Jun-26 | 09-Jun-26 | 09-Jun-26 | 20 | Completed | 100% | Interactive course details
9 | Week 9: Dev - Admin Dashboard
9.1 |  | Admin APIs |  |  |  |  | 10-Jun-26 | 16-Jun-26 | 16-Jun-26 |  | Completed | 100%
9.1.1 |  | Admin APIs | Build course CRUD admin APIs |  | 8.1.1 | moulik | 10-Jun-26 | 13-Jun-26 | 13-Jun-26 | 20 | Completed | 100% | Role guard auth checks
9.1.2 |  | Admin APIs | Build user activation API |  | 5.2.1 | moulik | 13-Jun-26 | 16-Jun-26 | 16-Jun-26 | 12 | Completed | 100% | Allows user block/unblock
9.2 |  | Admin UI |  |  |  |  | 10-Jun-26 | 16-Jun-26 | 16-Jun-26 |  | Completed | 100%
9.2.1 |  | Admin UI | Build course management admin UI |  | 8.2.1 |  | 10-Jun-26 | 14-Jun-26 | 14-Jun-26 | 24 | Completed | 100% | Forms for course adding
9.2.2 |  | Admin UI | Integrate database analytics charts |  | 9.1.1 | moulik | 14-Jun-26 | 16-Jun-26 | 16-Jun-26 | 16 | Completed | 100% | Visual learner metrics
10 | Week 10: Testing - Setup & Unit
10.1 |  | Unit Testing |  |  |  |  | 17-Jun-26 | 23-Jun-26 | 23-Jun-26 |  | Completed | 100%
10.1.1 |  | Unit Testing | Write Jest tests for React UI components |  | 9.2.1 |  | 17-Jun-26 | 20-Jun-26 | 20-Jun-26 | 16 | Completed | 100% | UI unit tests green
10.1.2 |  | Unit Testing | Write Pytest tests for FastAPI endpoints |  | 9.1.1 | moulik | 20-Jun-26 | 23-Jun-26 | 23-Jun-26 | 16 | Completed | 100% | API tests green
10.2 |  | Docs Setup |  |  |  |  | 17-Jun-26 | 23-Jun-26 | 23-Jun-26 |  | Completed | 100%
10.2.1 |  | Docs Setup | Generate & format Swagger API docs |  | 4.1.2 | moulik | 17-Jun-26 | 23-Jun-26 | 23-Jun-26 | 12 | Completed | 100% | Complete Swagger schema
11 | Week 11: Testing - Integration
11.1 |  | Integration tests |  |  |  |  | 24-Jun-26 | 30-Jun-26 | 30-Jun-26 |  | Completed | 100%
11.1.1 |  | Integration tests | Verify API calls in Postman runner |  | 10.2.1 |  | 24-Jun-26 | 30-Jun-26 | 30-Jun-26 | 16 | Completed | 100% | Contracts verified
11.2 |  | E2E Automation |  |  |  |  | 24-Jun-26 | 30-Jun-26 | 30-Jun-26 |  | Completed | 100%
11.2.1 |  | E2E Automation | Write E2E test flows in Playwright |  | 10.1.1 | moulik | 24-Jun-26 | 30-Jun-26 | 30-Jun-26 | 24 | Completed | 100% | E2E flow automated
12 | Week 12: Deployment & UAT
12.1 |  | Server Configuration |  |  |  |  | 01-Jul-26 | 07-Jul-26 | 07-Jul-26 |  | Completed | 100%
12.1.1 |  | Server Configuration | Configure AWS EC2 instance & Docker |  | 5.1.1 | moulik | 01-Jul-26 | 04-Jul-26 | 04-Jul-26 | 16 | Completed | 100% | AWS t3.medium setup
12.1.2 |  | Server Configuration | Setup secrets in GitHub Actions |  | 5.1.2 | moulik | 04-Jul-26 | 07-Jul-26 | 07-Jul-26 | 12 | Completed | 100% | CD configurations live
12.2 |  | User Acceptance |  |  |  |  | 01-Jul-26 | 07-Jul-26 | 07-Jul-26 |  | Completed | 100%
12.2.1 |  | User Acceptance | Coordinate UAT feedback (5 students) |  | 11.2.1 |  | 01-Jul-26 | 07-Jul-26 | 07-Jul-26 | 16 | Completed | 100% | UAT sign-off received
13 | Week 13: Handover & Closure
13.1 |  | Docs Completion |  |  |  |  | 08-Jul-26 | 15-Jul-26 | 15-Jul-26 |  | Completed | 100%
13.1.1 |  | Docs Completion | Finalise Report, Test Plan, LL Log |  | 10.2.1 |  | 08-Jul-26 | 12-Jul-26 | 12-Jul-26 | 24 | Completed | 100% | All documents compiled
13.2 |  | Project Closure |  |  |  |  | 08-Jul-26 | 15-Jul-26 | 15-Jul-26 |  | Completed | 100%
13.2.1 |  | Project Closure | Deliver final presentation to sponsor |  | 13.1.1 | moulik | 12-Jul-26 | 15-Jul-26 | 15-Jul-26 | 16 | Completed | 100% | Successful handover