## Test Plan
TEST PLAN
PROJECT NAME | campus finder-INDIA
PROJECT ID | IP-11170
SYSTEM NAME | WEB DEVELOPMENT
PROJECT MANAGER | HARSHADA TOPALE
This Test Plan describes the test strategy, objectives, schedule, resources, and deliverables for the EduSphere India project. Testing will be carried out to ensure the quality, functional correctness, and performance of the web platform, confirming that it meets all business and technical specifications before deployment.
• Frontend Web Application Pages (Homepage, About, Courses, Contact) • User Authentication & Authorization (JWT token registration and login flow) • Student Dashboard: Course enrollment, course listing, and progress tracking • Admin Panel: Course CRUD operations, user management, and dashboard reporting • RESTful API endpoints for backend modules • Responsive web design validation (Desktop, Tablet, Mobile layout) • Cross-browser testing (Chrome, Firefox, Safari, Edge)
• Native mobile applications (iOS/Android) • Production payment gateway integrations • Integrations with external third-party Learning Management Systems (LMS) • Performance/load testing exceeding 500 concurrent users
• 100% execution of all high and critical priority test cases • Minimum pass rate of 95% for all executed test cases • 0 critical or high-severity defects remaining in the production release • All pages load within 3 seconds under normal network conditions • Security validation showing zero susceptibility to OWASP Top 10 vulnerabilities (XSS, SQLi)
• Test Lead (Purna Sai Venkat): Test strategy planning, overall coordination, test report verification. • QA Engineers (Sravya Tepada, Sunay Potnuru): Test script writing, manual and automated test execution, bug reporting, and regression testing.
• Phase 1: Test Planning & Design (test plan creation, test case design) • Phase 2: Unit Testing (component validation using Jest & Pytest) • Phase 3: Integration Testing (API endpoint validation using Postman) • Phase 4: System & Regression Testing (E2E flows and regression cycles via Playwright) • Phase 5: User Acceptance Testing (UAT cohort review) • Phase 6: Test Closure & Handover (final reports)
• Unit Level: Component-level testing using Jest (React) and Pytest (FastAPI) • Integration Level: API and database layer testing using Postman collections • System Level: Full functional end-to-end flow testing using Playwright • UAT Level: Human-centric acceptance testing with the intern cohort
• Defect Tracking: Logged in a dedicated sheet with fields for ID, severity, priority, status, and assignee. • Severity Levels: Critical (show-stopper), High (core flow broken), Medium (workaround exists), Low (UI typo). • Priority Levels: Immediate (blocker), High, Medium, Low. • Lifecycle: New -> Assigned -> In Progress -> Resolved -> Retested -> Closed.
• Test Plan Document: Overall strategy and scope specification • Test Case Specification: Detailed steps and expected results • Defect Log / Bug Report: Log of active and resolved issues • Execution Summary: Summary statistics and sign-off report
• Jest & Pytest: Unit testing frameworks for frontend and backend components • Postman: API manual and integration testing • Playwright: Automated end-to-end browser regression testing • GitHub Actions: CI/CD integration for running tests on code commits • Chrome DevTools: Page load analysis and mobile layout emulation
• Operating Systems: Windows 11 (Dev workstation), Ubuntu 22.04 LTS (Staging server) • Browsers: Google Chrome, Mozilla Firefox, Microsoft Edge • Frameworks: React 18, FastAPI 0.111, PostgreSQL 15 • Network: Staging environment URL: https://staging.edusphere-india.com
• Database state is reset to seed data before executing system-level tests. • Critical path regression tests are run automatically on pull requests.
ITEMS TO TEST | TEST DESCRIPTION | EST START DATE | EST END DATE | RESPONSIBLE PERSON | STATUS | COMMENTS
Homepage | Verify homepage layout, responsive design, navigation links, and footer. |  | 14-Jun-2026 | moulik | PASS | Navigation and mobile responsiveness are fully functional.
User Auth | Verify registration, login with JWT token, password reset, and auth guards. | 15-Jun-2026 | 18-Jun-2026 | moulik | PASS | JWT storage and redirection work correctly.
Course Listing | Verify course listing page, category filters, and search functionality. | 19-Jun-2026 | 20-Jun-2026 | moulik | PASS | Search filter returns correct results.
Course Enroll | Verify student course enrollment, progress tracking, and dashboard updates. | 21-Jun-2026 | 22-Jun-2026 | moulik | PASS | DB enrollment records match and update successfully.
Admin Dashboard | Verify admin panel course creation, editing, deletion, and user activation. | 23-Jun-2026 | 26-Jun-2026 | moulik | PASS | Admin roles and course CRUD operations work.
API Endpoints | Verify GET /api/courses, POST /api/auth/login, and protected endpoint access. | 25-Jun-2026 | 28-Jun-2026 | moulik | PASS | Status codes and response structures verified.
Performance/Sec | Verify page load times (<3s), API response times (<500ms), and SQLi/XSS. | 29-Jun-2026 | 01-Jul-2026 | moulik | PASS | SQLi/XSS prevented; page load time is 2.3s.
UAT Testing | Conduct UAT sessions with the intern cohort and verify usability feedback. | 02-Jul-2026 | 05-Jul-2026 | moulik | PASS | Cohort feedback collected and sign-off received.